## Slide 2: Timeline of DPO Work
Feb 2023
Apr 2023
Jun 2023
Aug 2023
Oct 2023
Dec 2023
Feb 2024
Meeting in LA
PrePilot Data Delivered to
ID Manager/Arches
Meeting in DC
PrePilot Abandoned
Getty Notice IDs
in Wrong Format
5 Archival Items Loaded
5 Archival Items Reloaded
All Pilot Loaded
to IDManager/Arches (x2)
RCV Made Available
Learning ASpace, ID Manager, Arches
Design/code ID generation
Develop scripts
Prepare and Save PrePilot Test Images to DAMS
Pilot Digitization

## Slide 3: Turnaround by DPO
Feb 8 – DPO detects an error in the sequence of items
  “Item 0001 [appears as] item 8 in the folder” – Luis in Slack
  Diagnosed within minutes of detecting issue
  Error due to an autosorting statement in the query
Feb 13 – DPO loads all ID’s with the correct sequence
  50,100 IDs to ID Manager
  25,050 Records to Arches
2 business days

## Slide 4: “Slow” Script
Explained in meetings:
  Feb 6, JPC Tech Working Group
    Jeanine explained; Isabel and Andrew present
  Feb 12 meeting (organized by Michelle)
    Luis explained; Andrew present
SI -> Getty process changed at least 4x by Getty
  Kept scripts simple to reduce time in edits

## Slide 5: “Slow” Script Estimates in Parallel
ID’s of 25k images to ID Manager (50k IDs):
  X4: 74 mins
  X8: 37 mins
  X16: 19 mins
Not applicable for Pilot/Production
  Reload of all Pilot data

## Slide 6: Daily Estimates for Production
1k images/day (~160GB):
  Transfer from vendor to HDC (~40MB/sec): 70 mins
  Transfer to Hydra (limited to 20MB/sec): 140 mins
  Ingest to Osprey (in Hydra using 32 cores): 10 mins
  Visual QC by archivists: variable
  Transfer to DAMS hotfolder (~65MB/sec): 35 mins
  Creating ID’s in ID Manager/Arches: 20 mins
    Only manual step, to automate in Production
Notes: DPO can deliver in 24 hrs
Hydra:
- Sync between nearline and working: 36 mins
- Osprey: 10 mins
Limiting factors:
- Parallel stations by vendor
- QC by archivists
- DAMS ingest, can be reduced
- Hydra speed can be increased
What estimates we don’t have?
- Archive processing
- Surfacing of images via IIIF
- Andrew sending IIIF IDs to ID Manager
- Loading data to RCV, which is a manual process

## Slide 7: Daily Estimates
DPO can deliver in < 5 hrs
  Visual QC not included
Can keep up with ~5x output by vendor
Getty surfacing to RCV is not automatic
Notes: DPO can deliver in 24 hrs
Hydra:
- Sync between nearline and working: 36 mins
- Osprey:
Limiting factors:
- Parallel stations by vendor
- QC by archivists
- DAMS ingest, can be reduced
- Hydra speed can be increased
What estimates we don’t have?
- Archive processing
- Surfacing of images via IIIF
- Andrew sending IIIF IDs to ID Manager
- Loading data to RCV, which is a manual process

## Slide 8: Long-Running Scripts
Hydra Queues in 3 Time Limits:
  7 hours
  6 days
  30 days
OpenStreetMaps (from Geofabrik)
  3 days to process all continents